## Tasks
Day | Task Name | Status
Day 1 | PRD | Done
| Market Research | Done
| Github repo setup | Done
| Environment setup | Done
| Design Doc : Roadmap | Done
| Design choice evaluation | Done
Day 2 | RAG Ingestion (loader, chunker, vector store) | Done
| Agents Development (Document / Retrieval / Chat agents + Orchestrator) | Done
| FastAPI Endpoint development | Done
| Differentiator Feature: Retirement Planner module | Done
| Guardrails Implementation (input validation, prompt-injection defence, PII checks) | in-progress
| Evaluation framework code (RAGAS + DeepEval runners) | Done
| Run Evaluation on sample Q&A pairs + generate report | in-progress
| Observability setup (LangSmith tracing enabled & verified) | in-progress
| Logging implementation (app + error logs) | Done
| Production testing scenarios (failure cases, edge cases, malformed PDFs) | yet to start
Day 3 | Backend E2E testing | in-progress
| Code evaluation for design choices (review against PRD/Design Doc) | yet to start
| GitHub submission (push final code, clean commit history) | in-progress
| Frontend development (Streamlit UI) | Done
| Streamlit widget definition (forms, charts, buttons per page) | Done
| Integration — Connect frontend to backend agents / orchestrator | Done
| Serving through FastAPI (wire external clients to API layer + test endpoints) | in-progress
| UI & frontend testing | Not Started
| Full system end-to-end testing | yet to start
| Demo | yet to start
Day 4
Day 5